## Slide 1: ITEM – Proposal Summary

## Slide 2: Participants
The institutions that participate in the ITEM project
1

## Slide 3: Countries (in alphabetic order)
Austria
  UMIT – Private Universitat fuer Gesundheitswissenschaften)
Czech Republic
  CTU – Ceske Vysoke Uceni Technicke v Praze
Denmark
  AAU – Aalborg Universitet

## Slide 4: Countries (in alphabetic order)
Greece
  TEI of Crete – Technological Educational Institute of Crete
Israel
  HAC – Hadassah Academic College
  HIT – Holon Institute of Technology
  WIS – Wiezmann Institute of Science

## Slide 5: Countries (in alphabetic order)
Kosovo
  NSK – N. Sh. Kolegji Aga Xhite
  UoM – University of Mitrovica "isa Boletini“
  UoP – University of Prishtina
North Macedonia
  UKIM – Ss. Cyril and Methodius University in Skopje

## Slide 6: Countries (in alphabetic order)
Spain
  ULL – University of La Laguna
Sweden
  KSU – Karlstads Universitet
Uzbekistan
  KEEI – Karshi Engineering Economic Institute
  NUUz – National University of Uzbekistan
  TUIT – Tashkent University of Information Technologies

## Slide 7: Test Institutions
Uzbekistan
NUUz
Israel
HIT
HAC
TUIT
Kosovo
UoM
NSK
Rep. N. Macedonia
Greece
FINKI
TEI Crete
KEEI
UoP

## Slide 8: Timeline
2018-2021
2

## Slide 9: Project Stages
Preparation
Development I
Development II
Alpha phase
Preparing for full implementation
Full implementation
Finalize project

## Slide 10: Project Timeline

## Slide 11: Key Principles
Of the ITEM Project
3

## Slide 12: Key Principles
To increase students’ motivation, it is important to demonstrate to students that mathematics is crucial to their success
  By showing how math solves practical problems in their field of study

## Slide 13: Key Principles
It is important to identify students who are at risk to fall behind as soon as possible
  Frequent testing, tracking software

## Slide 14: Key Principles
Help students learn better
  Pair learning in class
  Gradually increase the difficulty level
  Mobile tools
  Visualizations

## Slide 15: Key Principles
Help teachers to teach better
  PBL, POPBL

## Slide 16: Key Principles
Help students who lack prior knowledge
  Prepare material needed for current classes
  Use available material

## Slide 17: Key Principles
Motivate
  Show relevance
  Build confidence
  Show that the staff cares and ready to help

## Slide 18: Key Principles
Build Supportive Infrastructure
  Administrative – identify students who need help and direct them to the help they need, flexibility
  Academic – gradually-paced material and classes for self study, mentors, special classes
  Assist students with special needs
  The student is not alone!

## Slide 19: Scope
Of the ITEM Project
4

## Slide 20: Scope of the ITEM Project
Two mathematics classes:
  Calculus 1 – single-variable calculus: differentiation and integration
  Linear Algebra 1 – up to eigenvalues, eigenvectors and SVD

## Slide 21: Scope of the ITEM Project
Prior knowledge
  Trigonometry (including inverse functions)
  Powers, exponentials and logarithms
  Fractions, , solve quadratic equations
  Graphics of basic functions

## Slide 22: Tasks
Of the ITEM Project
5

## Slide 23: Major Tasks
5.1

## Slide 24: Curricula
Linear Algebra
Calculus 1
Students who lack prior knowledge

## Slide 25: Supporting Methodology Documents
Teaching methodology document
Study guidelines for students
How to deal with students who fall behind

## Slide 26: Supporting Software
Visualizations and CAS tools
Prediction tool that tracks students at risk of falling behind
Automate tests and practice problems

## Slide 27: Meetings
Training seminars for teachers
Industry meet-up
Dissemination seminars

## Slide 28: Tasks
Management
5.2

## Slide 29: Ongoing Tasks – Management
1. Consortium Agreement
By December 2018
2. Form project’s management committees
By February 2019. Steering, Finantial and administration, Outcome implementation, Dissemination and sustainability, QA
3. Mathematica
By March 2019. Finalize the agreement with Mathematica and distribute the software to all test institutions in partner countries

## Slide 30: Ongoing Tasks – Management
4. Setup online management tools
By January 2019
5. Form agreements between the different institutions
By January 2019
6. Mobility grants
By February 2019
Apply for Erasmus Mobility grants for 2020

## Slide 31: Ongoing Tasks – Management
7. Semi-annual internal report #1
By April 2019
8. Coordinator manual
By May 2019
9. Semi-annual internal report #2
By November 2019
10. Progress report
By November 2019
Progress report to the EACEA

## Slide 32: Ongoing Tasks – Management
11. Semi-annual internal report #3
By April 2020
12. Semi-annual internal report #4
By November 2020
13. Mobility grants
By February 2021
Apply for Erasmus Mobility grants for 2021
14. Semi-annual internal report #5
By April 2021

## Slide 33: Ongoing Tasks – Management
15. Final Report
By November 2021
Final report to the EACEA
16. External audit report
By November 2021

## Slide 34: Ongoing Tasks – Management

## Slide 35: Tasks
Quality
5.3

## Slide 36: Ongoing Tasks – Quality
1. Performance
Quality of ITEM's management and collaboration
2. Educational material
Quality and completion of offline & online educational material
3. PBL and POPBL
Evaluation of the effectiveness of PBL and POPBL techniques

## Slide 37: Ongoing Tasks – Quality
4. Mobile educational devices
Assess the impact of mobile educational devices on students learning paths
5. Tracking software
Effectiveness of tracking software
6. Students who fall behind
Effectiveness of the methodology to deal with students who fall behind

## Slide 38: Ongoing Tasks – Quality
7. Training workshops for students
Evaluation of the quality of training workshops for students
8. Training workshops for teachers
Evaluation of the quality of training workshops for teachers
9. Website
Evaluation of project's website

## Slide 39: Tasks
Dissemination and Exploitation
5.4

## Slide 40: Ongoing Tasks – Dissemination and Exploitation
1. Online presence
Website, webpages and social media pages
2. Newsletters
Electronic news letters
3. Publications
Publications in international educational events

## Slide 41: Tasks: Phase 1
Preparation (15.11.18–14.6.19)
5.5

## Slide 42: Phase 1 – Preparation (15.11.18 –14.6.19)
1. Describe the topics to be integrated into the Linear Algebra and Calculus I curricula
2. Describe the format by which teaching material in Linear Algebra and Calculus I will be presented
3. Describe the methodology for measuring of baseline of mathematics knowledge and attitudes towards the subject

## Slide 43: Phase 1 – Preparation (15.11.18 –14.6.19)
4. Describe the requirements from the software that helps to identify students at risk of falling behind
5. Describe facilities in different institutions that can be built to help students that fall behind
6. Decide on a platform and scope of visualizations, mobile tools and CAS usage

## Slide 44: Tasks: Phase 2
Development (15.4.19–14.12.19)
5.6

## Slide 45: Phase 2 – Development (15.6.19 –14.12.19)
1. Measure (a baseline of) mathematics knowledge and attitudes towards the subject in participating institutions (both students and teachers)
2. Prepare teaching material to at least 60% of the topics identified in phase 1
3. Prepare the first version of the teaching guide to teachers who use the material developed

## Slide 46: Phase 2 – Development (15.6.19 –14.12.19)
4. Arrange and conduct the first workshop on applying PBL and POPBL techniques, as well as other project specific guidelines and recommendations (at AAU in Denmark)
5. Prepare automated frequent testing for at least 60% of the topics identified in phase 1
6. Prepare visualizations, mobile tools and CAS for at least 40% of the topics identified in phase 1

## Slide 47: Phase 2 – Development (15.6.19 –14.12.19)
7. Develop a prototype of the software that helps to early identify students who fall behind
8. Write the first version of the student manual on how to study math
9. Prepare the material for students who lack prior knowledge

## Slide 48: Phase 2 – Development (15.6.19 –14.12.19)
10. Prepare a methodology on how to deal with students who fall behind
11. Put all the material developed on a Moodle Asynchronous platform

## Slide 49: Tasks: Phase 3
Development II, Alpha (15.12.19–14.6.20)
5.7

## Slide 50: Phase 3 – Development II, Alpha (15.12.19–14.6.20)
1. Perform the first implementation (alpha test) of the methodology in three sites: one in Kosovo, one in Uzbekistan and one in Israel
2. Assess the implementation of the alpha test
3. Another baseline measurement of mathematics knowledge and attitudes towards the subject in participating institutions (both students and teachers)

## Slide 51: Phase 3 – Development II, Alpha (15.12.19–14.6.20)
4. Measure the attitudes mathematics knowledge and attitudes towards the subject in the alpha test sites
5. Prepare teaching material for all the topics identified in phase 1
6. Arrange the second workshop on applying PBL and POPBL techniques, as well as other project specific guidelines and recommendations

## Slide 52: Phase 3 – Development II, Alpha (15.12.19–14.6.20)
7. Prepare automated frequent testing for all the topics identified in phase 1
8. Prepare visualizations, mobile tools and CAS for all the topics identified in phase 1
9. Test the implementation of the software that helps to early identify students who fall behind

## Slide 53: Phase 3 – Development II, Alpha (15.12.19–14.6.20)
10. Prepare the material for students who lack prior knowledge
11. Participate in an Erasmus Week, held by TEI Crete
12. Put all the material developed on a Moodle Asynchronous platform

## Slide 54: Tasks: Phase 4
Prepare for full implementation (15.6.20–14.8.20)
5.8

## Slide 55: Phase 4 – Prepare for full implementation (15.6.20–14.8.20)
1. Update the teaching material based on the alpha test experience
2. Update the teachers' manual based on the alpha test experience
3. Update the students' manual based on the alpha test experience

## Slide 56: Phase 4 – Prepare for full implementation (15.6.20–14.8.20)
4. Update the frequent testing material based on the alpha test experience
5. Update visualizations, mobile tools and CAS based on the alpha test experience
6. Update the software that helps to early identify students who fall behind based on the alpha test experience

## Slide 57: Phase 4 – Prepare for full implementation (15.6.20–14.8.20)
7. Deploy the software that helps to early identify students who fall behind on all test sites
8. Update the material for students who lack prior knowledge based on the alpha test experience
9. Update the methodology on how to deal with students who fall behind based on the alpha test experience

## Slide 58: Phase 4 – Prepare for full implementation (15.6.20–14.8.20)
10. Update the material for students who lack prior knowledge based on the alpha test experience
11. Conduct the second workshop on applying PBL and POPBL techniques, as well as other project specific guidelines and recommendations (in Sweden)
12. Conduct the first workshop on teaching mathematics (in Austria)

## Slide 59: Tasks: Phase 5
Full implementation (15.8.20–14.6.21)
5.9

## Slide 60: Phase 5 – Full implementation (15.8.20–14.6.21)
1. Full implementation in all test sites
2. Assess the implementation of the full implementation
3. Another baseline measurement of mathematics knowledge and attitudes towards the subject in participating institutions (both students and teachers)

## Slide 61: Phase 5 – Full implementation (15.8.20–14.6.21)
4. Measure the attitudes mathematics knowledge and attitudes towards the subject in all the test sites
5. Participate in an Erasmus Week, held by TEI Crete

## Slide 62: Tasks: Phase 6
Project Finalization (15.6.21–14.11.21)
5.10

## Slide 63: Phase 6 – Project Finalization (15.6.21–14.11.21)
1. Assess the performance of the project
2. Update the teaching material based on the full implementation experience
3. Update the teachers' manual based on the full implementation experience

## Slide 64: Phase 6 – Project Finalization (15.6.21–14.11.21)
4. Update the students' manual based on the full implementation experience
5. Update the frequent testing material based on the full implementation experience
6. Update visualizations, mobile tools and CAS based on the alpha test experience

## Slide 65: Phase 6 – Project Finalization (15.6.21–14.11.21)
7. Update the software that helps to early identify students who fall behind based on the full implementation experience
8. Update the material for students who lack prior knowledge based on the full implementation experience
9. Update the methodology on how to deal with students who fall behind based on the full implementation experience

## Slide 66: Phase 6 – Project Finalization (15.6.21–14.11.21)
10. Update the material for students who lack prior knowledge based on the full implementation experience
11. Conduct the second workshop on teaching mathematics (in Spain)

## Slide 67: Tasks
By Institution
6

## Slide 68: TEI of Crete (Greece)
Coordination
Develop topics' material for Linear Algebra and Calculus 1
Advice: Material assisting to students who lack prior knowledge
Test site

## Slide 69: AAU (Denmark)
Training seminar
Teaching methodology document

## Slide 70: CVUT (Czech Republic)
Teaching methodology document
Study guidelines for students
Preparing material for Training Seminar

## Slide 71: UKIM (North Macedonia)
Develop topics' material for Linear Algebra and Calculus 1
Develop a prediction tool that tracks students at risk of falling behind
Automate tests and practice problems
Test site

## Slide 72: UMIT (Austria)
Develop a prediction tool that tracks students at risk of falling behind
Dissemination conference

## Slide 73: HIT (Israel)
WP Management
Develop topics' material for Linear Algebra and Calculus 1
Study guidelines for students
Advice: Develop a prediction tool that tracks students at risk of falling behind
Material assisting to students who lack prior knowledge
Test site

## Slide 74: HAC (Israel)
Develop topics' material for Linear Algebra and Calculus 1
Automate tests and practice problems
Visualizations and CAS tools
Test site

## Slide 75: WIS (Israel)
Advice: Teaching methodology document
Develop tools for measuring project's performance
Advice: Study guidelines for students

## Slide 76: NUUz (Uzbekistan)
Develop topics' material for Linear Algebra and Calculus 1
Automate tests and practice problems
Material assisting to students who lack prior knowledge
Test site

## Slide 77: TUIT (Uzbekistan)
Develop topics' material for Linear Algebra and Calculus 1
Automate tests and practice problems
Material assisting to students who lack prior knowledge
Test site

## Slide 78: TUIT (Uzbekistan)
Develop topics' material for Linear Algebra and Calculus 1
Automate tests and practice problems
Material assisting to students who lack prior knowledge
Test site

## Slide 79: UoM (Kosovo)
Develop topics' material for Linear Algebra and Calculus 1
Visualizations and CAS tools
Material assisting to students who lack prior knowledge
Test site

## Slide 80: NSK (Kosovo)
Develop topics' material for Linear Algebra and Calculus 1
Visualizations and CAS tools
Material assisting to students who lack prior knowledge
Test site

## Slide 81: KSU (Sweden)
Training Seminar
Industry Meet up
Teaching methodology document
Advice: Visualizations and CAS tools

## Slide 82: ULL (Spain)
Industry perspective on problems
Teaching methodology document
Advice: Visualizations and CAS tools
Advice: Material assisting to students who lack prior knowledge
Dissemination conference

## Slide 83: UoP (Kosovo)
Develop topics' material for Linear Algebra and Calculus 1
Visualizations and CAS tools
Material assisting to students who lack prior knowledge
Test site

## Slide 84: KEEI (Uzbekistan)
Develop topics' material for Linear Algebra and Calculus 1
Automate tests and practice problems
Material assisting to students who lack prior knowledge
Test site

## Slide 85: First Phase Dev
Suggestion for Discussion
7

## Slide 86: Group #1: Detailed Syllabi. Led by: HAC
Participants: All test institutions
Deadline: end of March
  Provide the syllabi of the courses in all test institutions – what topics are included
  Example of final exams
  Courses in which mathematics is applied
  Failure rates, dropouts rate, etc.

## Slide 87: Group #2: Deliverable Template. Led by HIT, TEI
Develop a template of how a deliverable of a topic would look like
  What material should be included?
  What format it is going to have?
  Supporting material to be included
  Show by example
  Based on the principles of the project

## Slide 88: Group #3: Suggesting Problems, Led by FINKI
Participants: All except WIS
Think about problems relevant to each one of the courses
  Calculus 1 for Electrical Engineering
  Calculus 1 for Computer Science
  Linear Algebra for Electrical Engineering
  Linear Algebra for Computer Science

## Slide 89: Group #4: Students who Fall Behind, Led by CTU
Participants: All test institutions
Describe facilities in different institutions that can be built to help students that fall behind
Strategies to deal with students who fall behind

## Slide 90: Group #5: Tracking Software. Led by Universum
Participants: Universum, FINKI, UMIT, HIT, TEI, ULL
Describe the requirements from the software that helps to identify students at risk of falling behind

## Slide 91: Group #6: Local Context. Led by UMIT
Background for teaching manual
Participants: UMIT, CTU, ULL, AAU
Timeline:
  Questionnaire by the end of March
  Answers by the end of April
  Report by the end of May

## Slide 92: Group #6: Local Context. Led by UMIT
Background for the teaching manual
  Learning philosophies in different institutions
  Cultural background in test institutions
  Challenges in different countries
  Ethical regulations in each test country

## Slide 93: Group #7: Tools. Led by ULL
Participants: ULL, test institutions
Decide on a platform and scope of visualizations, mobile tools and CAS usage

## Slide 94: Group #8: Quality. Led by WIS
Participants: WIS, UMIT, AAU, ULL, CTU
Decide on how to measure the outcomes